## Sheet1
|  |  | Dynamic Discovery & Scope of Work |  | Include | Content | Content Type |  |  | Labor Summary…
[5 empty] | 1 | Scope of Work Detail | Heading1 |  |  | Configured | Hours Adj | Total Hours | Type
|  |  | Discovery session date: | Please Enter | 0 |  | Paragraph |  |  | 0 | 0 | 0 | Tech |  | Overtime factor: |  | 1
|  |  | Total locations: | 1 | [5 empty] | 0 | 0 | 0 | Designer
[10 empty] | 0 | 0 | 0 | PM
|  |  | Solution Overview | [6 empty] | 0 | 0 | 0 | Trainer
[5 empty] | 1 | Tech Solutions, Inc. will implement the following solutions for Acme: | Paragraph
|  |  | Communication System | [5 empty] | Total Qty | Hours/Qty | Hours Adj | Total Hours | Type
|  |  | MiVoice Business communications system | 0 | 0 | MiVoice Business communications system | Bullet |  | 0 | 20 | 0 | 0 | Tech
|  |  | MiVoice Office communications system | 0 | 0 | MiVoice Office communications system | Bullet |  | 0 | 10 | 0 | 0 | Tech
|  |  | satellite systems networked to the main system | 0 | 0 | 0 satellite systems networked to the main system | Bullet |  | 0 | 4 | 0 | 0 | Tech
|  |  | MiVoice Border Gateway | 0 | 0 | MiVoice Border Gateway | Bullet |  | 0 | 8 | 0 | 0 | Tech
|  |  | Mitel Open Integration Gateway | 0 | 0 | Mitel Open Integration Gateway | Bullet |  | 0 | 4 | 0 | 0 | Tech
Devices
|  |  | IP phones | 0 | 0 | 0 IP phones | Bullet |  | 0 | 0.5 | 0 | 0 | Tech
|  |  | Analog phones | 0 | 0 | 0 Analog phones | Bullet |  | 0 | 0.25 | 0 | 0 | Tech
|  |  | Door boxes | 0 | 0 | 0 Door boxes | Bullet |  | 0 | 2 | 0 | 0 | Tech
|  |  | Speakerphones | 0 | 0 | 0 Speakerphones | Bullet |  | 0 | 1 | 0 | 0 | Tech
|  |  | Softphones | 0 | 0 | 0 Softphones | Bullet |  | 0 | 1 | 0 | 0 | Tech
|  |  | Consoles | 0 | 0 | 0 Consoles | Bullet |  | 0 | 4 | 0 | 0 | Tech
Applications
|  |  | Voice Mail | 0 | 0 | Voice Mail | Bullet |  | 0 | 4 | 0 | 0 | Tech
|  |  | MiCollab collaboration application suite | 0 | 0 | MiCollab collaboration application suite | Bullet |  | 0 | 4 | 0 | 0 | Tech
|  |  | Auto Attendant | 0 | 0 | Auto Attendant | Bullet |  | 0 | 1 | 0 | 0 | Tech
|  |  | Call Accounting | 0 | 0 | Call Accounting | Bullet |  | 0 | 6 | 0 | 0 | Tech
|  |  | e911 | 0 | 0 | e911 | Bullet |  | 0 | 4 | 0 | 0 | Tech
|  |  | Paging/Analog zones | 0 | 0 | Paging/Analog zones | Bullet |  | 0 | 1 | 0 | 0 | Tech
|  |  | Contact Center | 0 | 0 | Contact Center | Bullet |  | 0 | 4 | 0 | 0 | Tech
|  |  | Call Recording | 0 | 0 | Call Recording | Bullet |  | 0 | 3 | 0 | 0 | Tech
|  |  | IVR (Interactive Voice Response) | 0 | 0 | IVR (Interactive Voice Response) | Bullet |  | 0 | 8 | 0 | 0 | Tech
|  |  | Hospitality PMS integration | 0 | 0 | Hospitality PMS integration | Bullet |  | 0 | 4 | 0 | 0 | Tech
Enter Hours…
|  |  | Write-in application | 0 | 0 | Write-in application | Bullet |  |  |  |  | 0 | Tech
|  |  | Write-in application | 0 | 0 | Write-in application | Bullet |  |  |  |  | 0 | Tech
Carrier Services
|  |  | SIP channels | 0 | 0 | 0 SIP channels | Bullet |  | 0 | 2 | 0 | 0 | Tech
|  |  | PRI circuits | 0 | 0 | 0 PRI circuits | Bullet |  | 0 | 2 | 0 | 0 | Tech
|  |  | Analog trunks | 0 | 0 | 0 Analog trunks | Bullet |  | 0 | 0.25 | 0 | 0 | Tech
|  |  | Solution Diagram |  | 0 | Solution Diagram | Heading2+Break
[5 empty] | 0 | Below is a diagram showing the overall solution for Acme: | Paragraph
|  |  | Insert the network diagram here >>>>>>>>>> |  | 0 |  | ImageFile
Customer Responsibilities
[5 empty] | 5 | Customer Responsibilities | Heading2+Break
|  |  | Customer responsible for trunking changes | Yes | 1 | Customer will be responsible for ordering any local or long distance trunking changes as needed. Acme will not be responsible for delays, issues, or down time as a result of telco issues. | Bullet
|  |  | Customer will provide a point of contact | Yes | 1 | Customer will provide a point of contact that will be responsible for attending meetings, representing the customer changes, and making any necessary decisions. This individual will be our authority for making decisions even if they affect, due dates, financial repurcussions or changes in configuration and setup. | Bullet
|  |  | Customer will provide an extensions for all users | Yes | 1 | Customer will provide an extension list of all of their users. | Bullet
|  |  | Customer must provide information, tasks | Yes | 1 | Customer understands that there will be information, data, and tasks that need to be performed on their end by the date/time according to their project plan. Tasks or information that are not done in time will result in delays and will affect the installation date. | Bullet
|  |  | Project plan included? | Yes | 1 | See the Project Plan for further details about when information or tasks are due. The Project Plan also lists tasks that need to be performed by the Acme. | Bullet
|  |  | Who will set and test the phones? |  | 0 | No one will set and test the phones | Bullet
Network Responsibilites
|  |  | Network Information |  | 1 | Network Responsibilites | Heading2
|  |  | Standard Network Approach: | Yes | 1 | Our standard approach to include a Network Assessment, and work assumes proper security, access, and customer support as required | Paragraph
|  |  | Customer Provided Network Approach: | Yes | 1 | Customer will be responsible for the network requirements and for on-going maintenance including proper security, access, and customer support as required | Paragraph
|  |  | Data switch type: | None | 0 | Data switch type: None | Bullet
|  |  | Number of POE ports configured: | 0 | 0 | Number of POE ports configured: 0 included | SubBullet
|  |  | Number of POE ports provided: | 0 | 0 | Number of POE ports provided: 0 included | SubBullet |  | 0 | 1 | 0 | 0 | Tech
Professional Services
|  |  | Project Management |  | 1 | Project Management | Heading2
|  |  | Project Management: | Yes | 1 | Tech Solutions, Inc. will assign a Project Manager which will remain engaged throughout the life of the project. The Project Manager will be the main contact throughout the entire implementation process. | Paragraph
|  |  | Expected Project Duration (weeks): | 0
|  |  | Overtime |  | 0 | Overtime | Heading2
|  |  | Technician overtime (percent of hours) | 0% | 0 | 0% of technician hours are scheduled as overtime work for this project | Bullet
|  |  | Technician Sunday/Holiday (percent of hours) | 0% | 0 | 0% of technician hours are scheduled as Sunday/holiday work for this project | Bullet
|  |  | Post Cut Support |  | 0 | Post Cut Support | Heading2
|  |  | Cutover Support | 0 | 0 | 0 hours of remote post-cutover support will be provided | Bullet |  | 0 | 1 | 0 | 0 | Tech
|  |  | Technician Support Hours: | 0 | 0 | 0 hours of technician support will be provided Monday-Friday, 8:00am-5:00pm | Bullet |  | 0 | 1 | 0 | 0 | Tech
|  |  | Training |  | 0 | Training | Heading2
|  |  | Train the Trainer 4 Hour Classes: | 0 | 0 | Train the Trainer 4 Hour Classes: 0 included | Bullet |  | 0 | 4 | 0 | 0 | Trainer
|  |  | End-User Training 1 Hour Classes: | 0 | 0 | End-User Training 1 Hour Classes: 0 included | Bullet |  | 0 | 1 | 0 | 0 | Trainer
[5 empty] | 0 | Maximum (10) users per class | SubBullet
[5 empty] | 0 | Class length (1) hour with (.5) hour break | SubBullet
|  |  | Agent Training 1 Hour Classes: | 0 | 0 | Agent Training 1 Hour Classes: 0 included | Bullet |  | 0 | 1 | 0 | 0 | Trainer
[5 empty] | 0 | Up to (10) agents per class | SubBullet
|  |  | Supervisor Training 2 Hour Classes: | 0 | 0 | Supervisor Training 2 Hour Classes: 0 included | Bullet |  | 0 | 2 | 0 | 0 | Trainer
[5 empty] | 0 | Up to (4) supervisors per class | SubBullet
|  |  | System Admin Training 2 Hour Classes: | 0 | 0 | System Admin Training 2 Hour Classes: 0 included | Bullet |  | 0 | 2 | 0 | 0 | Trainer
[5 empty] | 0 | Up to (2) admin per class | SubBullet
Qty Calcd | Qty Adj | Part Number | Description |  | MSRP | Sell Price | Cost | Ext MSRP | Ext Sell | Ext Cost | Item Cat | Item Qty | Price Cat | Disc Cat | Rack Type | Rack Ht | Shelves | Volt Amps | MDF | Install Hrs | Design Hrs | Labor Cat | Vendor | ProductCat | WriteIn
0 | 0 | Tech | Technician Labor |  | 125 |  | 60 | [5 empty] | Services | [11 empty] | Y
0 | 0 | Designer | Designer Labor |  | 140 |  | 70 | [5 empty] | Services | [11 empty] | Y
0 | 0 | PM | Project Management |  | 150 |  | 75 | [5 empty] | Services | [11 empty] | Y
0 | 0 | Trainer | Training Labor |  | 125 |  | 60 | [5 empty] | Services | [11 empty] | Y
Hidden Section
Note on D1: JumpPoint
Note on D6: JumpPoint
Note on D42: JumpPoint
Note on D50: JumpPoint
Note on D57: JumpPoint
Note on A79: PartDetailSection
Note on A85: HiddenSection

## Temp Rangenames
CustomerName | Acme
SellerCompanyShort | Tech Solutions, Inc.